## Part 1 Benchmark
| ADMG Benchmark Assessment |  |  | Comments on DMP
Sunart Rainforest Deer Group
| Criteria | 2026 score | 2027 Score
1. Area and boundaries
| 1.1. Identify the appropriate boundaries for the group to operate in. | 3 |  | Appropriate boundaries and structure still to be confirmed
| 1.2. Define appropriate sub populations where applicable | 3 |  | Likely that area should be treated as one population.
2. Membership
| 2.1. All property owners with regular engagement in deer management within a deer range should be members of a DMG, including private and public land owners. | 5 |  | Interest and engagement with current process is actually very good. Still to be decided if properties should be members of a DMG, or just attendees at a forum.
| 2.2 DMG should have process to accommodate those properties who might not wish to become full members, but for whom DMG communications are useful, and whose input, however small, might be useful to DMG. These might include crofters, agricultural occupiers, owners of small woodlands and others on adjoining land where deer might be present or where they may create impacts. | 5 |  | Local comms are good, and people who need to be accommodated largely already are.
3. Meetings
| 3.1. DMGs should meet regularly. Two formal meetings per year is the norm but more frequent interaction between members, between meetings, should be encouraged. | 4 |  | , although too many to be sustainable going forwards.
| 3.2. For effective collaborative management to take place it is important that all DMG Members should attend meetings where possible, or be represented by someone authorised to make appropriate decisions on their behalf. | 5 |  | Attendance is very good.
| 3.3 Public sector landholdings should be members of DMG, as above, and contribute to the running of the group. | 5 |  | Good input from Nature Scot, FLS and SGRPID
| 3.4. In addition to landholding Members, including public sector owners, public agencies such as Nature Scot or the National Parks should be in attendance and other relevant authorities such as Police Scotland or Scottish Forestry may be invited to attend DMG meetings as appropriate to particular circumstances. | 5 |  | Good input from Nature Scot, FLS and SGRPID
| 3.5. Meetings should operate to an agenda and be accurately minuted. Attendees should be encouraged to participate and agreed actions and decisions should be recorded. | 5 |  | Administration is good, supported by part time employee of Sunart CC
| 3.6. Group can demonstrate a capacity to deal with issues between meetings as they arise, and to provide an ongoing source of communication and advice as required. | 5 |  | Works well at moment. Good range of skills and advice available to group.
4. Constitution & Finances
| 4.1. All DMGs should have a Constitution which defines the area of the Group, sets out its purpose, its operating principles, membership and procedures, in addition to providing for appointing office bearers, voting, raising subscriptions and maintaining financial records | 2 |  | Group yet to decide how they actually want to be structured.
| 4.2. Good management and budgeting of finances | 3 |  | Group has access to a lot of funding at the moment. Although there are processes and structure in place to deal with that, the project seems to be going ahead at a speed that some are uncomfortable with.
5. Deer Management Plans
| 5.1. All DMGs should have an up to date, effective and forward looking Deer Management Plan (DMP) that is endorsed by Group members and Nature Scot. | 3 |  | Deer plan currently in development, yet to be endorsed
| 5.2. The DMP should record all the land management objectives within the DMG area. | 4 |  | Objectives set out, although final mix yet to be agreed.
| 5.3. Where applicable, the plan should include a rolling 5 year population model, and this should be updated on an annual basis allowing for actual culls, recruitment and mortality. | 3 |  | Population modelling used, but data required incomplete, and models need to be properly tested yet.
| 5.4. Appropriate use of maps to illustrate relevant detail. | 5 |  | Good use of maps
| 5.5. The DMP should identify the public interest aspects of deer management as set out in WDNA. | 5 |  | DMP sets out full range of public interest within the area
| 5.6. DMP should make appropriate reference to other species of deer within the DMG area, and provide a level of detail proportionate to this interest. | 5 |  | Appropriate reference made
| 5.7. It should include a list of actions/ Action Plan that deliver the collective objectives of DMG Members as well as public interest objectives. | 4 |  | Actions listed, yet to be endorsed
| 5.8 Roles within the DMG for delivering the all agreed actions should be clearly assigned. | 3 |  | At present, interim Chair and secretary positions have been delegated, but group will need a more formalized structure going forwards.
| 5.9 These actions should be updated annually or as appropriate. | 3 |  | Actions are still draft as yet
| 5.10. It is important that all DMG Members should play a full part in the planning process and in the implementation of agreed actions | 3 |  | Participation is good, but implementation yet to be reviewed against list of actions.
| 5.11. The DMP may identify potential conflicts and how they can be prevented or addressed. | 4 |  | Good indication of basic potential conflicts. Less clear on how they will be addressed.
| 5.12. Relevant local interests should be consulted on new DMPs and advised of any changes as they come forward. | 4 |  | Good level of local consultation to date
6. Code of Practice on Deer Management
| 6.1. The Code should be endorsed by all DMGs and referenced in both the Constitution and Deer Management Plan of every Group. The terms of the Code should be delivered through the Group Deer Management Plan. | 5 |  | Included in relevant documents
7. ADMG Principles of Collaboration
| 7.1. The Principles of Collaboration should be incorporated into all DMG Constitutions and Deer Management Plans. | 5 |  | Included in relevant documents
8. Best Practice
| 8.1. All deer management should be carried out in accordance with Best Practice. | 5 |  | Training standards in area appear to be very good.
| 8.2. All Deer Management Plans should reference and follow WDBP which will continue to evolve. | 5 |  | Training standards in area appear to be very good.
9. Data and Evidence gathering- Deer counts
| 9.1. Accurate deer counting forms the basis of population modelling. An ethos that reflects this should be in evidence | 3 |  | The 2025 drone count assessed what was on open hill at the time, but the greater part of the population was likely uncounted. Little previous modelling done on population, and discipline to do this needs to be fostered going forwards.
| 9.2.DMGs should aim to carry out a regular well planned coordinated foot count of the whole open range deer population. The norm is to count annually or biannually where terrain permits. | 3 |  | The 2025 drone count assessed what was on open hill at the time, but the greater part of the population was likely uncounted. Little previous modelling done on population, and discipline to do this needs to be fostered going forwards.
| 9.3 Where foot counts are not practicable, or where additional or better information is sought, the DMG is able to work with Nature Scot to deliver a suitable schedule of helicopter counts, raising funds to do so where this is appropriate. | 3 |  | The 2025 drone count assessed what was on open hill at the time, but the greater part of the population was likely uncounted. Little previous modelling done on population, and discipline to do this needs to be fostered going forwards.
| 9.4. Recruitment counts should be undertaken annually for the purposes of population modelling, and these should be sufficient to inform any significant variations across the DMG area. | 1 |  | Not obvious that these elements are given much consideration at present.
| 9.5 The DMG should look to assess mortality where this is deemed to be in excess of normal levels, and population models adjusted accordingly. | 1 |  | Not obvious that these elements are given much consideration at present.
| 9.6. Other census methods may be required in some circumstances, e.g. dung counting in woodland or other concealing habitats or on adjoining open ground. | 4 |  | FLS undertake density assessments in their woodland area
10. Data and evidence gathering- Culls
| 10.1. All DMGs should agree a target deer population or density which meets the collective requirements of Members without any significant detriment to the public interest. | 2 |  | These elements have got to be properly developed yet.
| 10.2 The target density should be appropriate to achieving the objectives set out, and this agreed with SNH. | 2 |  | These elements have got to be properly developed yet.
| 10.3. The cull should be apportioned among Members to deliver the objectives of the DMP and individual management objectives while maintaining the agreed target population and favourable environmental condition. | 2 |  | These elements have got to be properly developed yet.
| 10.4 DMG can collate and distribute relevant cull data as required prior to spring meeting. | 5 |  | The current Epicollect system is excellent for tracking and presenting cull data, and FLS can forward cull info as required.
| 10.5. The Group cull target should be reviewed and, if necessary, adjusted annually. | 2 |  | These elements have got to be properly developed yet.
11. Data and evidence gathering- Habitat Monitoring
| 11.1. DMGs should have an ethos of monitoring habitat impacts across their range. | 4 |  | The ethos required to keep track of what is going on certainly exists, with good survey information from 2024 & 25.
| 11.2. Deer Management Plan should contain appropriate detail on methods and procedures. | 4 |  | Covered in deer plan
| 11.3. The HIA undertaken should be effective and appropriate to the purpose for which it is being undertaken in both extent and frequency of sampling points. | 2 |  | These elements still require to be developed and implemented properly. Review progress and update in 2027
| 11.4. The DMG should be undertaking HIA on an appropriate cycle. | 2 |  | These elements still require to be developed and implemented properly. Review progress and update in 2027
| 11.5 The DMG should be able to collate, analyse and present data in an appropriate manner | 2 |  | These elements still require to be developed and implemented properly. Review progress and update in 2027
| 11.6 The DMG should agree impact targets on the range of appropriate habitats with Nature Scot. | 2 |  | These elements still require to be developed and implemented properly. Review progress and update in 2027
| 11.7 The DMG should be able to compare impacts against targets set. | 2 |  | These elements still require to be developed and implemented properly. Review progress and update in 2027
| 11.8 The DMG is able to adjust deer populations based on HIA results | 2 |  | These elements still require to be developed and implemented properly. Review progress and update in 2027
| 11.9 The DMG collects information on the numbers, distribution and impacts of other herbivores that are relevant within the area. | 5 |  | Plan presents good insight in to other pressures
12. Competence
| 12.1. It is recommended that in addition to DSC 1 deer managers should also attain DSC 2 or equivalent. | 5 |  | Very strong in this area
| 12.2. Deer managers supplying venison for public consumption are required to certify carcasses as fit for human consumption to demonstrate due diligence. “Trained Hunter” status is required for carcass certification. | 5 |  | Very strong in this area
13. Training
| 13.1. All DMGs should have a training policy and incorporate it in the DMP | 5 |  | Strong areas for Sunart
| 13.2. The training policy should promote and record continuing development through Best Practice Guidance. | 5 |  | Strong areas for Sunart
| 13.3 DMG should maintain an audit of relevant skills so that any training requirement within the group can be readily identified. | 5 |  | No audit as such, but current situation is very good
14. Venison Marketing
| 14.1. Membership of the Scottish Quality Wild Venison scheme is recommended by ADMG. | 2 |  | Only FLS achieve this standard
| 14.2. There is evidence of collaborative venison production within the Group, but acknowledging that physical geography and distances may often mean that this is not possible. | 4 |  | Informal collaboration takes place locally, with one local processor.
15. Communications
| 15.1. DMGs should include a Communications Policy in their DMP. External communication should be directed at parties not directly involved but with an interest in deer management including individuals, local bodies such as community councils, local authorities, local media and other specialist interests. This policy should be implemneted and be appropriate to the DMG area | 3 |  | Work in progress. Policy included within deer plan.
| 15.2. Minutes of DMG meetings should be accessible and publicly available. | 2 |  | Deer related minutes not obviously available online
| 15.3. A Deer Management Plan should be accessible and publicly available. | 5 |  | Draft deer plan available online on dedicated page.
| Total | 210 | 0
| Total as a % | 72.4138 | 0
5 | Delivery of this element is particularly good within this DMG
4 | Delivery is generally good, in line with standard
3 | Delivery is partial or incomplete and requires support or oversight
2 | Delivery is generally poor, but some level of delivery and engagement is present
1 | Delivery is poor or there is no engagement on this issue.

## Part 2 Deer Management Planning
n/a